State of Alabama

Traffic Safety Information System (TSIS)

Strategic Plan 2015-2020

July 1, 2015

# Table of Contents

Table of Contents	1

Executive Summary	2

1.0  Background and History	5

2.0  TSIS Plan Vision	7

2.1  General 25 Year Backdrop Vision	7

2.2  Five-Year Vision	11

3.0  TSIS Stakeholders	14

4.0  Alabama Traffic Records Assessment	16

4.1  TRA Section 1: Management and Planning Recommendations	18

4.2  TRA Section 2: TSIS Component Recommendations	20

5.0  Planned Projects	24

5.1  Overview and Organization	24

5.2  Project Specification	25

5.3  TSIS Measurable Performance Indicators	36

STATE OF ALABAMA

TRAFFIC SAFETY INFORMATION SYSTEMS (TSIS)

STRATEGIC PLAN

# Executive Summary

This document presents the Alabama Traffic Safety Information Systems (TSIS) Strategic Plan for the 2015-2020 time period, or planning horizon.  This is a five year plan that will be initiated, upon approval, sometime during CY2015.

The plan begins by providing context in terms of the overall background and history of the planning process over the past decades.  Alabama’s Traffic Safety Information System (TSIS) components include all of the hardware, software and data needed to generate information that impacts either the frequency or the severity of traffic crashes.  Just the definition of these various files and systems is an enormous project, and the problems involved in coordinating the inter-agency activities to support safety decision-making creates serious issues in every state.  The large number of agencies involved at both the state and local levels include a wide range of activities throughout the traffic safety community, including collection, editing, forwarding, data entry, processing and the distribution of information that is generated.

The document continues by recognizing that any effective planning process must begin with a vision.  This vision in turn defines the goals that the implementation of this plan will attempt to accomplish over the next five years.  Because the TSIS itself is quite diverse, the vision of its accomplishments over the next five years is also quite diverse.  It a combination of all TSIS components with the most advanced technology that is anticipated to become available and feasible to implement over the next five years.  It strives not only to advance the technology base being applied to each of the components, but to integrate these components into a cohesive system that can serve the data generation, data storage, case management, and analytics required to serve both the operational and the planning/research needs for information.

This is followed by a discussion of the roles of the various TSIS stakeholders within the state, which include the Alabama Department of Economic and Community Affairs (ADECA); the Alabama Criminal Justice Information Center, the Alabama Administrative Office of Courts and the Alabama Department of Public Safety, which have now be consolidated into the Alabama Law Enforcement Agency (ALEA); the Alabama Department of Transportation (ALDOT); the Alabama Department of Public Health (ADPH); the Alabama Department of Revenue (ADOR); and local law enforcement, departments of transportation, hospitals and emergency services.  Federal stakeholders include the National Highway Safety Administration (NHTSA); the Federal Highway Administration (FHWA); and the Federal Motor Carriers Safety Administration (FMCSA).  As members of the TSIS, all of these stakeholders provide input to the plan as well as engaging in discussions for its improvement and final approval.

The following gives a summary of the plan according to the six components into which they were organized:

- Citation and Adjudication Component includes the extension and roll out of the electronic citation, a proposed DUI defendant intake system, a method for moving digital information directly to the field officers using available cell phones, a statewide Internet-based incident reporting network, and technological advances to make the traffic citation reporting and processing system totally paperless.

- Crash Component includes the complete roll-out of eCrash, further integration of GIS capabilities into eCrash and CARE, the generation of an updated Crash Facts Book, and the development of the Alabama Dashboards for Visualization Analysis and Coordinated Enforcement (ADVANCE) to produce a more effective interface to deliver CARE-generated information.  This will also require a second version of eCrash to be developed based on the availability of automated location systems and feedback as to improvements needed to make the eCrash data entry system more effective and improve data quality.  Longer term plans call for a system to allow the public to report potential crash incidents, the development of a centralized (enterprise) CARE system, the development of an advanced collision diagramming system, and the development of software that will enable the generation of hotspots based on GIS coordinates.

- Driver Component calls for more effective driver licensing information (including pictures) to be distribution to the field through the extremely successful Law Enforcement Tactical System (LETS).  This will require a more effective Driver History database, which is updated automatically by eCrash and eCite, to be available to officers in the field via an upgraded MOVE system.  It will also entail PI&E projects that will address drivers transitioning to vehicles with advance crash prevention systems.  Finally, a study is proposed to identify methods by which driver and other records can be protected against fraudulent uses.

- EMS-Medical Component includes continued support for the implementation of the National Emergency Medical Services Information System (NEMSIS), an ambulance stationing research project, the development of a spinal injury database, and a pilot project to reduce EMS delay time to the scene of crashes with a moving map display.  This will be accomplished by the implementation of the Mobile Officers’ Virtual Environment (MOVE) in EMS vehicles and the processing of trauma center and EMS run time data through CARE and ADVANCE.  Finally, a project to develop the First Responder Solution Technique (FIRST) seeks to provide Law Enforcement agencies with quick, accurate, and location-aware inventory of available emergency medical assistance facilities.

- The Roadway Component involves a wide diversity of projects in support of the State’s IHSDM/HSM/SA initiatives.  This will include the integration of roadway features into CARE and the integration of Crash Modification Factors (CMFs) into the CORRECT system using the facilities of the CMF Clearinghouse.  To effectively locate crashes on the roadway, it is essential that ALDOT complete their various projects along these lines so that they can be integrated into eCrash and used by CARE to fully utilize its GIS displays capabilities.

- Vehicle Component plans include the development and roll-out of an electronically readable vehicle registration card and a statewide distribution network that will make vehicle information immediately available to all consumers of these data in the state, including the LETS system.  Other projects call for an online insurance verification system (OVIS), and the development of the data infrastructure to support crash avoidance and ultimately driverless vehicles.

- Integration and Information Distribution Component, which was added to the other functionally oriented categories above, considers those projects that transcend and have the goal of integrating and/or producing/distributing information from several databases.  A major effort is proposed to populate the current Safe Home Alabama web portal so that it will integrate all of the information generated by all agencies and present it in one unified source to the traffic safety community.  An example of this is the proposed new Safety Portal that will be a hub for all traffic safety and related data analytics.  General TSIS management activities are also included in this component as are general innovations of MOVE and the use of mobile platforms for MOVE and its applications.  Integration is also necessary for the Data-Driven Approaches to Crime and Traffic Safety (DDACTS) that are now being recommended by various federal agencies.  Finally, a number of ETLs will be developed to enable the integration of crash, citation, roadway, EMS/injury and vehicle data so that analytics can be performed on these datasets to generate information that is not currently available.

The Project Specification Section of this document is the heart of the five-year plan in that it gives a high level view of the planned projects in each of these areas.  A final section contains the TSIS measurable performance indicators for each of the projects given in the project specification section.

# 1.0  Background and History

Alabama’s Traffic Safety Information System (TSIS) components include all of the hardware, software and data needed to generate information that impacts either the frequency or the severity of traffic crashes.  Just the definition of these various files and systems is an enormous project, and the problems involved in coordinating the inter-agency activities to support safety decision-making create serious issues in every state.  The large number of agencies involved at both the state and local levels include a wide range of activities throughout the traffic safety community, including collection, editing, forwarding, data entry, processing and the distribution of generated information.  More recently the impact of case management systems in addition to the crash case have come into the purview of the state’s TSIS.  Examples of these include the state’s electronic citation (eCite), which begins with the issuance of an electronic citation and proceeds electronically through the court system to ultimately impact the driver history record.  Alabama’s Model Impaired Driver Access System (MIDAS) is another example, which intensively tracks alcohol and drug impairment cases from citation through treatment or incarceration.

These issues began to be addressed in Alabama when the National Highway Traffic Safety Administration (NHTSA) awarded Alabama a contract in July 1994 to coordinate and facilitate the creation of a strategic plan for traffic information systems within the state.  The first step in this process was the performance of a Traffic Records Assessment (TRA) for the state of Alabama.  The major result of the TRA was a set of over 50 recommendations for improving the traffic information system, which became the basis for the state’s Strategic Plan.  Two subsequent TRAs have been conducted for the state, the most recent was completed in February 2011.  Subsequent strategic plans have responded to recommendations from this assessment.

The following are the key events that have driven the planning process over the past decade:

- The Alabama Traffic Information Systems Council (ATISC) was created in 1994 as a prerequisite to obtaining funding from the National Highway Traffic Safety Administration (NHTSA) for the original Strategic Planning project.

- The Alabama Traffic Records and Safety Committee (ATRSC) was formed and had its first meeting on May 3, 2000.  It commissioned the update to the Traffic Records Assessment and the Strategic Plan.

- The Alabama Traffic Records Coordinating Committee (TRCC) was organized with a membership to include policy level representatives of the key safety data systems within the state.  Membership included the data managers, data collectors, and major data users for each of the following system components: Traffic Crash, Roadway Inventory, Citation/Adjudication, EMS/Injury Control, Driver License/Driver History, and Vehicle Registration and had its first meeting on March 28, 2006.  The State TRCC prescribed by Section 405c should have the authority of overseeing the planning and improvement of the key safety data systems within the state. The State TRCC will be expected to approve the strategic plan and implementation plan on an annual basis.

- A Traffic Safety Information System (TSIS) five year plan was developed in 2006 and updated with minor changes every year thereafter.  With these slight modifications, that planning document has provided guidance over the past five years on all TSIS efforts.  That plan was forward looking and has served quite well in bringing into existence several new and revolutionary systems, including CARE ADVANCE (dashboard interfaces), eCite and eCrash.

- A five-year plan was developed after the February 2011 Traffic Records Assessment conducted by NHTSA.  It reflected their recommendations but went on to specify definitive actions that not only address the issues cited but build upon the many commendations that were made in that document.

- The five year plan was updated to the 2013-2018 planning horizon in response to the MAP-21 format for qualification for the 405c funding cycles in 2013.  The strategic plan was approved at that time by NHTSA, and the current document is an update for the 2015-2020 planning horizon.

# 2.0  TSIS Plan Vision

TSIS coordination activities are required in the areas of crash records, emergency response and other medical records, traffic citations, roadway characteristics (construction, maintenance, traffic volumes, etc.), driver history, vehicle history and other demographic data.  The coordination of this planning process is a microcosm of the overall ongoing coordination that is required to move the state ahead effectively in applying information technology to its transportation systems.  Through a series of meetings, individual efforts and contacts, information was submitted and synthesized into the plan.

## 2.1  General 25 Year Backdrop Vision

It is difficult to summarize such a comprehensive planning process in a nutshell.  However, any effective planning process must begin with a vision.  This vision will define the goals that the implementation of this plan will attempt to accomplish over the next five years.  However, in its effort to move Toward Zero Deaths (TZD), which has been adopted in both the ADECA/NHTSA Highway Safety Plan (HSP) and the ALDOT/FHWA Strategic Highway Safety Plan (SHSP), the TRCC determined that this five year vision must fit into a more futuristic view of traffic safety over the next 25 years.  In this regard the goal set consistent with TZD was a reduction of traffic fatalities by to no more than 50% of its current value.

In this regard, the following vision items are looking forward to the year 2040 and the evolution of traffic records that will take place over the next 25 years:

- The TRCC will be the primary movers of the effort to move toward a surface transportation system that will be fully integrated in its automated communications both among vehicles and with the highway system.

- Driverless vehicles will become the norm, and those that are not driverless will be heavily automated with safety devices and communications to either avoid or prevent traffic collisions.

- The TRCC will work much closer with the auto industry especially from the sociological point of view of leading the traffic safety community in this direction.  The possibility of TZD will be recognized, if not its actual realization.

- With this leadership of the TRCC and the traffic safety community in general, the innovations required will not be resisted by the general public, but will be welcomed as part of an accepted and inevitable evolution to TZD.

- This evolution has already begun in some of the higher level vehicles and they are advertising crash prevention systems, computer controlled braking systems, visualization systems, lane-departure and forward collision warning systems, obstacle detection systems, adaptive cruise control, and electronic stability control.

- Current innovations can be subdivided into: (1) in-vehicle crash avoidance systems that provide: (a) warnings to the driver and/or (b) limited automated control of the vehicle; (2) connected communication technologies: (a) vehicle-to-vehicle (V2V), and (b) vehicle-to-infrastructure (V2I); and (3) autonomous (i.e., self-driving) vehicles, examples of current prototypes include the Google car and Volvo platoons.

- V2I communications, currently the least developed, will either inform drivers or alter autonomous vehicle operations in the following devices or conditions: traffic signals, weather conditions, traffic congestion, work zones, and potential hazards (e.g., potholes).

- Data from V2I and V2V systems will provide traffic management centers with detailed, real-time information on traffic flow, speeds, and other vehicle conditions, enabling the anticipation of traffic incidents and improved responses to them.

- The major commercial airlines have gone through entire years without a single fatality, and the reason quite clearly is technology, and the infrastructure for that is data and analytics.  We need to continue this theme – “TZD is only possible if we get the driver out of the loop.”

- The next step is using current technology to get vehicles to automatically communicate with each other (without human intervention) and the use of platooning lanes (or entire highways) where these platoons can travel at extremely high speeds and total safety (or something at least comparable to the airline industry where a crash becomes a major news event).

- Safety and increased traffic flow will both be accomplished by these innovations since platooned vehicles can theoretically travel as a unit (like a train) only a few feet apart but at very high speeds.  While the ultimate goal might be automated platooning (perhaps transparent to the occupants of any given vehicle), the immediate use of automated communication will be to promote safety and traffic flow in a subset of the vehicles on the road (perhaps only a few to start with).

- The increased speed and safety will provide incentives for people to purchase “platoon-ready” vehicles that qualify to use these highways and lanes – much like current HOV lane.  This could providing major acceleration to the evolution because it is really a fairly small step to go from platooning with a designated special lead vehicle to platooning with a volunteer lead vehicle, the ultimately, no lead vehicle at all.  This will evolve as the technology is developed.

- One reason that the sociological aspects of this evolution are so important is that costs will be nominal with economies of scale, much as airbags are not considered a major cost in vehicles today.

- Some recent surveys indicated considerable skepticism about autonomous vehicles on the part of the general public.  As traffic records and traffic safety professionals, promotion is the role we must play.  We should be able to see both the feasibility of it all and its ultimate value.  Recent issues with distracted driving have been a major setback to moving things forward safety wise – as have marijuana laws and just the culture in general.  The value of getting the driver out of the critical role of controlling the vehicle is the only hope for TZD.

- This evolution will sneak up on us if we do not see that this is going to cause a major shift in our data efforts.  Crash data are going to become less important as the technology produces fewer and fewer crashes, and the emphasis will shifts from improving the driver to improving the vehicle technology with the goal of eliminating the driver altogether.

- We must take preemptive steps to minimize the emergence of an anti-technology culture, since those who do to adapt will have their jobs (and status) threatened.  So, we cannot assume that everyone is on board here, and in fact, we wonder it this entire line of reasoning is being questioned because it would seem that it really has very little to do with traditional traffic records as we know them.  Issues such as the capabilities to hack vehicle computer systems must be dealt with proactively.

- Population will increase up to an additional 40 million placing a corresponding increase demand upon the roadway system.  To some extent this effect will be moderated by a growing demand of millennials to avoid commutes by living in large metropolitan areas, by a dramatic increase in tele-commuting, and by a continued exponential increase in on-line shopping.

- The modes of transportation will change with pedestrian and bicycle travel increasing dramatically, and ride-sharing and cycle sharing becoming much more accepted, as well as new and innovative transit options.  Specialized autonomous vehicles will replace taxis for high demand shuttle routes.

- The longer life expectancy and the aging of the population will result in a further increased demand for autonomous vehicles.

- Law enforcement will use drones, advanced GPS and satellite imagery and other advanced technologies as an integral part of their operations to supplement their efforts.

- Some of the major changes in the Traffic Records community to be expected over the next 25 years:

  - A dramatic de-emphasis on crash records since ideally as TZD is realized they will become rare or non-existent.

  - An increase the more intensive multi-disciplinary crash investigations (MCDI) will become more predominant emulating the aviation establishment.  Considerable efforts will be required to make data from such investigations useful, in stark contrast to the MDCIs of the past in which each cases tended to be an end in itself.

  - A corresponding de-emphasis on driver behavior will take place as the driver is eliminated from the picture; the emphasis will turn to technological defects in the integrated vehicle-roadway systems.

  - Because of fewer crashes there will have to be increased data sharing throughout the country in order to get a sufficient sample sizes within subsets of the data to do effective analytics.  Data analytics will move away from the historical (e.g., crash and citation) approach toward methods that are more predictive in nature (e.g., fault tree analysis), and more proactively addressing emerging safety risks.

  - Technology will be directed toward the vehicle, and the state traffic records specialists will need to form alliances with companies or trade associations within their regions to support the efforts to compare alternative technologies to assure that the evolution away from the driver is being controlled in an optimal manner.

  - Emphasis will dramatically increase to efficient and effective roadway innovations that will be needed to support the driverless effort.  As examples, rail-vehicle crashes should become virtually impossible, as should intersection crashes.  Very few vehicles will ever have to stop at red lights except where the traffic volume is extreme.

  - Intelligent roadways will complement and supplement the driverless vehicle, and because roadways have traditionally been managed by government (as opposed to private industry management of vehicle manufacture), there will be a demand for government IT personnel to transition to this growing need.  The transition will be from crash records analysis to the analysis of real time data being accumulated from V2V and V2I communications systems.

  - The need for additional cyber security will challenge IT personnel to acquire the expertise involved to assure that the hardware and software that they deploy is able to dynamically adaptive to these aggressively innovative threats.

  - Backup redundancy is essential to the reliability of GPS-dependent systems that can currently be disrupted by weather events, demand overload, jamming and spoofing by hackers, and excess system demand.  This could be one of the greatest technological challenges in moving the autonomous vehicle capabilities forward, in that it will require a holistic approach requiring expertise across the spectrum of the transportation enterprise.

  - Violation types will dramatically change with the driver out of the picture; there will need to be a transitioning of enforcement personnel to testing the various aspects of the technology within the vehicles.

  - Similarly, EMS/medical efforts and resources currently consumed on traffic crashes will be allocated to providing the technology to enable EMS to get to other types of emergencies in reduced time through automated routing that dynamically adjusts in real time to changing conditions.

  - Integrated traffic safety and land use planning will demand a broader range of expertise on the part of systems analysts and software designers.

  - Additional IT resources will be required to support the current emphasis on traffic safety metrics that will continue and will be extremely useful in guiding traffic safety decisions so that traffic safety resources obtain the maximum benefit in saved lives and reduced injury.  Enhanced data and analytics will be required on the location and conditions of infrastructure as well as the location and characteristics of safety incidents.

  - The ubiquitous nature of personal computerized cell phone devices by law enforcement officers and the general public will lead to hundreds of apps that have not yet be conceived of.  For example, we can see a seamless multi-modal plan dynamically guiding long distance travelers.  Law enforcement capabilities will include automated continuous dynamic updating of weather and other potentially disastrous events, complete integration with first responder and recovery enterprises, and most importantly, effective communication linkages with each other and with the general public.

  - As the proportion of connected and automated vehicle-roadway systems continue to increase, a major change in the traffic records community will be essential to address the evolving policy requirements, to manage evolving data, and to mitigate privacy and liability concerns.  Ideally, these systems will be able to identify, diagnose, and anticipate breakdowns in all aspects of the resulting complex technological systems. Finally, there should be no small concern about the need to develop preemptive countermeasures that will protect these systems from malicious attacks and the resulting tragedies that would result.

Some of the above concepts were obtained from: www.dot.gov/beyondtraffic.

## 2.2  Five-Year Vision

It is not expected that all of the above factors will be reflected in the five year plan.  The above is intended to provide the backdrop view that will follow well after the proposed five year plan is implemented.  However, it is important to have the longer term view when considering the activities planned in the immediate and intermediate future.  The following is the five-year vision that was adopted by the TRCC that provides the high level guidance to the planning process; this summarizes what is expected at the end of the five year planning horizon:

- All police and EMS vehicles (both state and local) will be equipped with laptops or other equipment that will enable the direct entry and retrieval of all relevant records (e.g., including crashes, citation, criminal and medical records).   A common virtual environment within all of these vehicles will facilitate not only data entry and use, but also communications of imagery, GIS coordinates and other information to provide complete coordination and interoperability among first responders and subsequent rescue units for such events as traffic, weather and terrorist emergencies.

- Global Positioning System (GPS) and Geographical Information Systems (GIS) technologies will enable officers and EMS personnel to automatically enter accurate locations directly into their respective crash, citation, EMS run and all other records that require location specification.  By clicking the location on automated maps all of the necessary data will be accurately added to the records making unnecessary any further map or table lookup or other data entry (e.g., the route number or road name).  This capability will be available to all law enforcement statewide to be used in any of their systems requiring location specification.

- Systems will be available in each unit to optimally map out quickest routes and alternative routes to emergencies around congestion.  The system will contain and artificial intelligence capabilities that will modify alternative routes based on past approved experiences.

- Digital data and imagery will be pushed to both the central dispatch and local command cells where they are most needed to deal with emergencies such as weather events or hazardous materials catastrophes.  Field inputs will be designed to enable officers to provide these data elements in a minimal time and effort on their part.  Data will be piped back to them from all involved officers so that both the central and distributed commands can have not only situational awareness, but there will be full perception of resource availability so that resources can respond to emergency situations in the most effective way possible.

- Bar coding and electronic encryption on drivers' licenses, vehicle registrations and other identification cards will enable accurate and complete driver and registration data to be entered automatically and directly into the all records that consume these data elements.

- All citizens above the age of 15 will have STAR ID with a capability of adding data to their identification cards to meet a variety of traffic safety and other social and economic needs, including identification, authentication, and system/facility access.

- All citation, crash, EMS and other records will be submitted electronically on consistent and integrated data entry systems, and the data will be automatically uploaded to the central databases, saving considerable data entry costs and resulting in totally complete and consistent records that are readily available for analysis and case management.

- Data generated will be immediately available at the local levels to planners and countermeasure developers.  Analytics software will be provided to enable them to obtain any information contained in these data to define problem locations, perform problem identifications, and formulate improved countermeasures on a continuous basis.  The ultimate goal will be to provide an analytics capability in the field in real time and to train field officers in some of the basics of its use.

- Data generated will also be piped to virtual real-time dashboards that will enable administrators to monitor and control their projects, and to view information generated from their respective systems in a wide variety of ways that respond to their operational needs.  These dashboards will be fully customizable so that, by default, they will see a common view of the performance metrics for their systems in real time for any time frame.

- Dashboards will be developed for mobile systems such that they can be set to default to the most useful information that is needed by the field officer on a daily/hourly basis.  In addition, they will provide the interface to more detailed alternative information that is currently not available on web-based dashboard systems (e.g., IMPACT analyses).

- A centralized index of all available databases will exist that will enable users of these data to understand the availability and content of these databases and to access the data needed for both planning and operational purposes.

- A system will exist to integrate the various disparate databases.  For example, GIS will enable the roadway characteristics data to be merged with crash data to provide the basis for surfacing those roadway characteristics that have the maximum potential for crash frequency and severity reduction.  Databases will have the ability to be integrated by any common key.

- Case number cross references will enable the merging of crash and medical/EMS data to enable optimal deployment of EMS resources and the development of new countermeasures.  In the interim, key data elements in the EMSIS and Trauma data systems will be used to merge these data.  Crash, EMS (ambulance run), and trauma data will have an integration capability that is both deterministic and probabilistic, depending on the data availability.

- The FHWA Highway Safety Manual (HSM) and Interactive Highway Safety Design Manual (IHSDM), along with the AASHTO Safety Analyst systems, will be implemented to the extent that they are seen to improve both (1) the safety of overall roadway designs, and (2) the ability of the current Cost-benefit Optimization for the Reduction of Roadway Caused Tragedies (CORRECT) to produce roadway improvements that produce the maximum safety benefits.  This will necessitate that roadway characteristics are made available to roadway designers and high crash location investigation teams as required by the systems and manuals listed above.

- A system will be developed and deployed by ALDOT that will totally integrate the maintenance and safety roadway improvement project so that when assets are deployed for roadway maintenance they can be leveraged to produce roadway improvements over the entire segment being maintained; this has been found to reduce the cost of otherwise pure safety project to the extent that the benefit-cost ratios for such roadway improvements are at least doubled.

- Internet portals that include both analytical and GIS capabilities will enable any and all of this information to be viewed on virtually any computer in use.  This increased visualization in the form of maps will enable decision-makers to visualize and better understand the true nature of problems, especially those which go beyond solutions at point locations and involve comparative analysis over relatively long segments.

- A more intuitive user interface, including wizards, will be developed for CARE and the CARE Dashboard systems that will enable anyone who is computer literate to immediately obtain information directly from this system without prior training.

- A unified approach to court records will exist such that the violation, court referral, alternative sentencing and criminal histories will be available to all courts and other authorized officials throughout the state in real time.

- All traffic safety efforts within the state will be recorded for and published in a common web site that will provide a reference back to the various web sites of the agencies and service organizations that are performing these activities.  Called SafeHomeAlabama.gov, this web site will be kept current by efforts of members of all of the participating organizations.

- An improvement in demographics data will be made available to all uses of technology in the State via SafeHomeAlabama.gov to enable them to formulate countermeasure approaches using crash rates by severity in addition to raw frequencies.

- There will be a major effort throughout the traffic safety community led by the Traffic Records Coordinating Committee and other Information Technology specialists to recognize the feasibility of ultimately removing the driver from the critical role of vehicle control.  The shift of emphasis toward recognizing that the Toward Zero Deaths (TZD) goal can only be achieved by these developing technologies is itself a major challenge that must be faced by technology specialists.

While this scenario might seem futuristic, all of the technology needed to implement it is currently available.  This plan will enable this technology to be rolled out throughout Alabama in a systematic way, while taking advantage of the successful pilots in Alabama and throughout the country.

# 3.0  TSIS Stakeholders

The TSIS Strategic Plan is a mechanism to attain the coordination that is essential to the goal of optimal traffic safety resource allocation.  It is a working document that can and should be continuously updated and adapted to system development needs as they come into better focus.  Its immediate objective is to document a plan for developing those technological advances that can be implemented within Alabama to best advance the cause of traffic safety.

With such a large complex system involving literally hundreds of data sources and thousands of data elements administered by dozens (but involving hundreds of different) agencies, one might ask if coordination is even possible.  The answer depends entirely upon the willingness of each of the involved individuals to put aside departmental interests in order to attain the goal of maximizing the safety interests of the state’s roadway users.  To this end, the Alabama Traffic Records Coordinating Committee (TRCC) has the responsibility to coordinate the many interdepartmental development efforts that are expected to be forthcoming from this plan.

The following agencies participate in TRCC and share coordination responsibilities for traffic safety and their corresponding information systems:

- Alabama Department of Economic and Community Affairs (ADECA), which is charged with the overall planning responsibilities for traffic safety in general, including various plans (e.g., Impaired Driving, Seatbelts, Selective Enforcement, etc.) including this TSIS strategic plan:

- Alabama Law Enforcement Agency (ALEA).  This agency became operational in 2014 as an umbrella agency subsuming all of the law enforcement functions that were previously being performed throughout all state agencies.  Two agencies that were commonly referenced individually in previous TRCC five-year plans will now be reference collectively as ALEA:

  - Alabama Criminal Justice Information Center (ACJIC) will continue to be a major contributor to TSIS systems within the DPS Information Technology Division; these contributions include taking the primary role in developing the Mobile Officer’s Virtual Environment (MOVE), the Uniform Crime Reporting (UCR) Local Template for Reporting and Analysis (ULTRA), the Law Enforcement Tactical System (LETS), and the Centralized Agency Management System (CAMS) all of which have been documented in detail in previous TSIS strategic plans;

  - Alabama Department of Public Safety (DPS) will continue to responsible for the collection of violation and crash data, and is the custodian of several databases in this regard (henceforth referenced as State Trooper Division of ALEA or “State Troopers;”

- Alabama Administrative Office of Courts has coordination responsibilities for all of the courts, which involves violation, adjudication, and criminal (including driver) histories;

- Alabama Department of Transportation, which is responsible for building and maintaining safe roadways, and has also recently assumed responsible by federal legislation for a wide variety of countermeasures that are not roadway related;

- Alabama Department of Public Health, which has jurisdiction over all Emergency Medical Services, hospital, and trauma registry data;

- Alabama Department of Revenue, which handles the vehicle registration functions;

- Local police, departments of transportation, hospitals and emergency services;

- National Highway Safety Administration (NHTSA), which has had general responsibility for driver and vehicle countermeasures;

- Federal Highway Administration, which has in the past been mainly focused on roadway engineering countermeasures, but has recently been given flexibility by federal legislation for the distribution of other countermeasure funding as well; and

- Federal Motor Carriers Safety Administration, which has interests in commercial vehicle and driver safety.

The purpose of listing these agencies is to demonstrate the immense problem involved in coordinating the development of an effective statewide traffic safety information system.  Coordination is quite difficult even within many of the larger of these state departments.  In the past there were very few formal inter-departmental procedures established to organize and operate the data systems.  Most of the essential interactions between agencies have been handled with informal relationships between individuals within the departments who had common traffic safety information interests.  Little, if any, of this interaction has been dedicated to the design and development of systems for the future.  Also, diminishing resources have tended to put a strain on some of the informal relationships that have served the state so well in the past.

# 4.0  Alabama Traffic Records Assessment

In January 2011, Alabama hosted a team of traffic records experts for the third NHSTA-sponsored assessment of traffic records and traffic information system in the state.   This review was particularly helpful in that;

- Outside experts critically reviewed the six major component areas (Crash, Roadway, Driver, Vehicle, Citation and Statewide Injury Surveillance)  of traffic information systems and offered commentary on their functions

- The assessment drew the attention of the state’s traffic records community and involved them in the assessment as it was on-going.  The impromptu planning sessions that occurred after a component was reviewed was very beneficial.

While the entire assessment is included in the appendix, a brief summary of the findings are presented here.

Overall the assessment team found that Alabama had made significant progress in meeting the goals of a modern traffic record system as formulated in the earlier Plan and guided by the state’s Traffic Records Coordinating Committee (TRCC).

In recent years, Alabama has made major advancements in the use of technology to timely and accurately capture data for Citations and Crashes with the use of electronic citation (eCite) and eCrash field applications.   These applications now account for reporting over 90% of the respective activities in these areas.  Indeed, Alabama has implemented a nearly paperless process for both crash report and traffic citations.  With the application of the Critical Analysis Reporting Environment (CARE) to these data streams, traffic safety professionals and the public have a reporting tool that provides the critical analysis of the data.

Alabama has also maintained adequate Roadway, and Driver’s and Vehicles Data Systems that are in regular use by the community.  Again, the Assessment Team, while making recommendations in these areas, found these systems met the requirement of the traffic safety community and the standards suggested by NHSTA.

In the area of Statewide Injury Surveillance System (SWISS) Data Component, the Team recommendations were the most numerous as coordination and improvements in this area have seen the slowest advancements.  Despite the shortcomings in this area, Alabama has had significant improvement in two areas:

- Emergency Medical Services Information System (EMSIS) has been deployed and is electronically collecting data from all licensed EMS agencies.

- A statewide trauma registry is being developed by building upon the well-established Alabama Head and Spinal Cord Injury Registry (AHSCIR).  Alabama’s SWISS component is lacking in data from statewide emergency departments and hospital discharge data.

Finally, in the area of Traffic Record System Management, the Team found that Alabama had an effective structure utilizing a two-tiered Traffic Records Coordinating Committee (TRCC).  The Team did recommend that Alabama employee a full-time Traffic Records Coordinator to further advance the work of the TRCC.

A list of the critical needs was established by the 2011 Traffic Records Assessment.  This was updated with a progress report on each recommendation for a recent review by the TRCC.  The status of each TRA recommendations will be given in the following format:

- The recommendation itself exactly as in the February 4, 2011 TRA;

- An indicator of overall status given by one of the following:

  - Completed

  - Significant progress; completion is imminent

  - Acceptable progress

  - Initiation; project is in the initiation stage

  - On hold; being given serious consideration but the item has not yet been initiated.

- A brief description of the reason for the indicator given above.

The status indicator will be given in bold to provide a demarcation between the TRA recommendation and the status explanation.  The review is in two sections: (1) management and planning; and (2) traffic records system components.

## 4.1  TRA Section 1: Management and Planning Recommendations

#### 1-A: Traffic Records Coordinating Committee

- Hire or assign a full time Traffic Records Coordinator.  Acceptable Progress.  Terry Henderson is functioning as the Traffic Records Coordinator on a part-time basis with the assistance of the University of Alabama Center for Advanced Public Safety (UA-CAPS) to provide logistical and technical support.  This is covering the functional requirements of a full time coordinator; adding someone a dedicated full time person to perform this function is cost-prohibitive.

- Perform a Quality Improvement Training Needs Assessment for the TRCC members.  Significant progress.  The TRCC considered this at their April 3, 2014 meeting and determined that a subcommittee should be created that would perform the needs assessment by a survey of the TRCC members.

- Review all systems for current deficiencies.  Significant progress.  This is ongoing as is seen in the updates to the Alabama Traffic Safety Information Systems (TSIS) Strategic Plan.  All updates of existing systems reflect our ongoing review of deficiencies.  A major effort in this regard to update and improve the quality of eCrash data is being undertaken at the writing of this document.

#### 1-B: Strategic Planning

- Charge the TRCC with the development of a new Strategic Plan for Traffic Records Improvement addressing the deficiencies and recommendations in this report.  As previously performed with the development of the original TSIS, assure that all TRCC members participate in the development of the Plan and the selection and priority setting of the projects in the Plan.  Completed.  The TRCC is required to approve all changes in the Strategic Plan.  The Strategic Plan is being updated on at least an annualized basis and the TRCC is involved in both the updates and approving the final result.

- Charge the Traffic Records Coordinator with the development of a progress reporting system and the continual monitoring and reporting of progress status of projects included in the TSIS Strategic Plan and the Section 405c grant program. The progress report should be shared with all TRCC members.  Acceptable progress.  Progress reports, all of which relate to the Strategic Plan are presented at each TRCC meeting, and are available in the minutes of these meetings.  In addition, the current document is being updated to reflect recent developments.

- Develop a formal quality control program addressing all components of the traffic records system.  Initiation.  This is a vague requirement that could require extensive resources if performed centrally for all components of the traffic records system.  However, QC groups within each of the respective custodial agencies are being formed (if not already ongoing).  An example is the recently formed eCrash QC group that was formed to review all data elements in eCrash by comparing pre- and post-eCrash data element values.  This group will shortly initiate updates for at least a dozen data elements being collected by eCrash.

#### 1-C: Data Integration

- Work with agency stakeholders through the TRCC to address information sharing obstacles and develop a plan to address these concerns with the goal of sharing non-identifying information across the traffic records system enterprise.  Significant progress.  The projects within this current TSIS Strategic Plan consider a number of integration items that demonstrate a degree of data sharing that goes well beyond this recommendation.  However, the ideal degree of integration has not been achieved, so this is an ongoing process and will not be marked as completed.

- Develop an outreach plan to demonstrate the use of integrated data files in CARE in an attempt to promote data integration efforts and encourage agencies to share their data with other traffic system stakeholders.  Acceptable progress.  While a formal plan has not been documented, there are continuous attempts being made, as demonstrated by the recently-approved Strategic Plan, to expand the use of CARE in all areas and aspects of traffic safety.  An internal Concept Paper has been developed in terms of the further growth and development of CARE applications.  A short-term objective is to re-write this document so that it can be distributed to the entire traffic safety community within the state.  An assignment was made to this effect at the April 3, 2014 meeting of the TRCC.

- Conduct a Privacy Impact Assessment, if not already done, to address information sharing issues and develop agreements for standard information sharing policies among traffic system component stakeholders.  Completed.  A Confidentiality Agreement (CA) has been developed to resolve issues of data confidentiality.  This has resolved most of the confidentiality issues with regard to data sharing, with the possible exception of medical data.  Those working with medical data are subject to HIPAA compliance rules, which are being observed by all involved.

#### 1-D: Data Uses and Program Management

- Expand the use of the CARE warehouse to include other government users and researchers.  Significant progress.  See the Integration section of the updated TSIS Strategic Plan.  We do not see any time in the near future when this will be able to be considered as completed.  Efforts to expand CARE will be made over the next decade, the goal being to add at least two significant traffic safety databases per year.

### 4.2  TRA Section 2: TSIS Component Recommendations

#### 2-A: Crash Data Component

- Transition the remaining 14 law enforcement agencies to either the eCrash system or provide technical assistance to their RMS vendors to accept their crash report format into eCrash as soon as possible.  Significant progress.  Birmingham has converted over to eCrash, and we are expecting that the proportion of eCrash submissions will exceed 100% by the end of 2014.  DPS has stated that they will stop accepting paper forms.

- Seek a funding mechanism to provide the MapPoint software for all law enforcement agency patrol vehicles so GIS location data can be collected universally for all crashes.  If successful, eliminate the requirement for the officer to provide link-node data on the eCrash report.  Completed.  We believe that the TRA Team meant “MapClick” as opposed to “MapPoint” in that MapPoint is a commercial package and they would not recommend any specific commercial package.  However, the intent of this recommendation has been completed and the project is underway (i.e., funding has been obtained) to develop and implement the MapClick system for locating crashes and all other events and objects within the State.  While the securing of funding has been completed, the complete transition of all eCrash locations to MapClick has not, and this will take several more years for the local agencies.  However, all of DPS units are now on MapClick, and the number is growing for total statewide implementation (anticipated to be 95% by January 1, 2017).

- Encourage through the TRCC those traffic records custodial agencies that do not provide their files to CARE to do so citing the benefits to them and the overall traffic records community.  Significant progress.  See the Integration section of the TSIS strategic plan.  Several agencies have been contacted and are providing their data.  Some agencies have been deferred due to the lack of resources; the TRCC does not want to commit to an agency until it is sure that there are adequate resources available to follow through on the efforts necessary to put a database under CARE.

- Engineer into eCrash additional edits to address more specifically the accuracy of the data collected where feasible.  Significant progress.  In the past these were dealt with as they are detected.  An excellent example is the recent modification in the eCrash data entry system to accommodate distracted driving.  This data element was grossly under-reported due to its competition with all of the (non-mutually exclusive) contributing circumstances.  A new data element was developed at the crash level and it enables officers to mark this cause for all crashes that in any way involved distracted driving.  Another effort to identify and address all issues that could be but are not currently being resolved by edit checks is currently underway and we see it being extremely successful in the next planning horizon.

- Conduct an evaluation of the quality of the eCrash dataset based not on the number of automated field completion errors found but on the overall accuracy of data after report approval. Note: this is to identify if there is a false sense of security in the automated validation process by those actually approving reports.  Initiation.  While it is extremely difficult for the TRCC to see how this would be accomplished without significant funding to obtain the data for it, the current QC efforts include the comparing of all variable values being produced by eCrash with their counterparts that have been produces over the past ten years by the paper data entry forms.  This effort shows great promise for a major improvement in eCrash data quality.  It should be noticed that faults detected will be addressed in three ways as a result of this effort: (1) changes and deployments to eCrash per se, (2) changes in the ETL that translates raw eCrash data to that processed by CARE, and (3) law enforcement officer training.

- Develop a tracking system to ensure all fatal crash occurrences are identified and submitted to the FARS unit for inclusion into the FARS program.  Completed.  Mr. Bill Shanks at the DPS FARS unit has in place such a tracking system.

- Create a quality review oversight process for statewide eCrash reports to ensure that report content conforms to a uniform standard procedure regardless of the agency authoring the report. Implement within eCrash a capability to produce periodic data quality reports. This needs to be separate from the existing automated error checking process and should concentrate on accuracy and consistency in reporting across all jurisdictions.  Initiation.  The current QC effort for eCrash has demonstrated that the same approach can be used to evaluate the quality of local data entry.  This will be accomplished by performing IMPACTs over all variable comparing a local area (e.g., a city) to all comparable areas within the state.  Outliers will be evidence of improper reporting and will be followed up on.

#### 2-B: Roadway Data Component

- Charge the Traffic Records Coordinating Committee (TRCC) to fast track a project to develop a uniform location reference system for all public roads.  Significant progress.  ALDOT is giving this its highest priority, and CAPS is continuing to develop the infrastructure for MapClick at the local levels.

- Create an enterprise roadway information system that will serve the information needs of ALDOT executives to manage the transportation assets for safety and mobility.  Acceptable progress.  ALDOT has a Comprehensive Project Management System (CPMS) for this purpose that deals with past, current and planned projects.  This system needs to be augmented with an inventory of transportation assets.  Work is in process to create such a database.

#### 2-C: Driver Data Component

- Determine if there is a legal constraint prohibiting the recording of adverse histories of serious offenses when licensing non-CDL drivers from other states. If so, explore opportunities to change the constraint. If not, compose a listing of serious offense convictions that are reasonable for Alabama to retain from a previous state of record.  Examples recommended include the following: DUI/DWI, speeding in excess of 25mph over the posted limit, aggressive driving, reckless driving, driving while unlicensed, making improper or erratic lane changes, and others Alabama considers serious.  Completed.  The state maintains a driver history database of all violations from which the most severe can be extracted.

- Determine whether suspending licenses based on a DUI arrest (admin per se) independent of the judicial processing of those cases provides a significant benefit in view of the current requirement to rescind those suspensions when a court dismisses the charges or finds the defendant not guilty.  Significant progress.  A system has been developed to address the rescission of the paper forms, which was approaching 40%.  The beta test involved 37 AST-60 reports that were created to date of which there were no rescissions.  Further steps are still required in terms of total statewide implementation.

#### 2-D: Vehicle Data Component

- None

#### 2-E: Citation/Adjudication Data Component

- Examine, through the TRCC, means by which to include the remaining small percentage of paper tickets into the State central database to ensure a comprehensive picture of the enforcement activity statewide.  Acceptable progress.  Efforts are continuing to extend the benefits of eCite to all municipalities.  This is an ongoing effort that is expected to continue over several years.  It is not something that can be mandated.  However, as local jurisdictions see the advantages of eCite, they are systematically adopting it.

- Integrate the MIDAS system with the driver license system to develop a flag that indicates a driver whose license is suspended or revoked is eligible to reinstate due to compliance with court orders or, minimally, require that prior to reinstatement of a driver privilege or license, the Driver License Division personnel ensure the MIDAS system shows that a driver has completed all court requirements for re-licensure.  On hold.  This will be investigated with AOC during the 2014 calendar year.

- Survey law enforcement agencies to determine those who share common records management vendors to provide for economies of scale in contracting for programming to integrate records management systems with eCrash and eCite systems provided by the State of Alabama.  Significant Progress.  An assignment was made to initiate such a survey at the April 3, 2013 meeting of the TRCC.

- Use data generated by the MIDAS system to determine if the administrative sanction for driving under the influence can be changed to improve its effectiveness.  On hold.  This will be investigated with AOC during the 2014 calendar year.

#### 2-F: Statewide Injury Surveillance System (SWISS) Data Component

- Develop annual reports on trauma and motor vehicle crashes to be available on the ADPH website.  Completed.  Very flexible reports are available through the current CARE system.  It also enables data export that can also be used to generate very flexible reports.  A number of standardized reports have also been developed that contribute to this purpose.

- Promote the use of EMSIS and Alabama Trauma Registry (ATR) data as an injury prevention tool to the public, public safety professionals, and researchers.  Acceptable progress.  As these systems have been brought under CARE their accessibilities have increased.  There are certainly other professionals who can use these capabilities and efforts will continue to be made to assure that their benefits are extended to them.

- Make EMSIS and ATR data available through an online query tool by incorporating it into CARE or similar program.  Completed.  These capabilities are now available.

- Explore the possibility of collecting dispatch information from BLS/Rescuer providers and 911 calls.  Completed.  This was discussed at the April 2014 meeting of the TRCC and it was determined that it would be impossible to obtain this information (at least at this time with our current technologies) from the Basic Life Support (BLS) providers.  On the other hand, it was recommended that the Advanced Life Support providers would have much greater potential for obtaining immediate benefits.

- Conduct a review of trauma centers to ensure all ATR eligible cases are being submitted.  Completed.  This is constantly under review by the DPH, and they know the percentage of eligible cases being submitted and are making every effort to get this up to 100%,

- Develop a method of integrating EMS information into ATR electronically from EMSIS and eliminate the need for entry from paper forms.  Acceptable progress.  A project has been launched to develop an EMSIS-compliant data entry system that is freely available to all EMS providers.

- Explore the possibility of requiring all hospitals to submit all ATR eligible cases.  Initiation.  A project has been initiated to pre-populate the trauma registry case files with EMS run data.  This project will provide the basis for obtaining the ATR case data.  It is expected, however, that there will be no way to require such data; it will be provided voluntarily.  This will provide the pilot for ultimately requiring all hospitals to submit their ATR cases.

- Ensure adequate representation on the TRCC by members from all components of the SWISS.  Completed.  Current membership is fairly comprehensive; the TRCC will continue efforts to involve all interested parties.

- Develop an emergency department and hospital discharge databases. Completed.  These databases currently exist.

- Develop a means to share information on motor vehicle crashes fatalities between vital records, FARS, and the Driver License Division.  Completed.  CARE currently provides these capabilities.  Further educational efforts are required, however, to assure that this capability is known of by the appropriate people, and that they are trained on CARE sufficiently to enable them to use these systems.

# 5.0  Planned Projects

## 5.1  Overview and Organization

It is impossible to make the major changes envisioned over the next five without significant impacts on current operations.  Thus, it is essential that these changes be phased in over the next five years to minimize this downside.  This plan is the first step in that direction.  It should not be considered a static end in itself.  Rather, it is a working document that can and should be updated on a regular basis and especially as progress is made.  Some of the items planned are already in the process of being implemented, and the purpose for their inclusion in this plan is to see that these items are brought to completion.

The following gives a summary of the plan according to the six components into which they were organized:

- Citation and Adjudication Component includes the continued extension and roll out of the electronic citation, an improved DUI defendant intake system, a method for moving digital information directly to the field officers using available cell phones, a statewide Internet-based incident reporting network, and technological advances to make the traffic citation reporting and processing system totally paperless.  This interacts heavily with the MIDAS upgrades that are discussed in the driver component.

- Crash Component includes the complete roll-out of eCrash, further integration of GIS capabilities (e.g., the MapClick system) into eCrash and CARE, the generation of an updated Crash Facts Book, and the development of the Alabama Dashboards for Visualization Analysis and Coordinated Enforcement (ADVANCE) to produce a more effective interface to deliver CARE-generated information.  This will also require a second version of eCrash to be developed based on the availability of automated location systems and feedback as to improvements needed to make the eCrash data entry system more effective and improve data quality.  Also proposed is a voluntary crash reporting system for deer strikes.

- Driver Component calls for more effective driver licensing information (including pictures) to be distribution to the field through the extremely successful Law Enforcement Tactical System (LETS).  This will require a more effective Driver History database that is updated automatically by eCrash and eCite.  There will also be a major integration effort for the purpose of generating analytics from the integration of the driver history records with crash, eCite, and other databases.  This component will also include upgrades to the impaired driver access system (MIDAS), and the NCIC incident/arrest system (ULTRA).

- EMS-Medical Component includes continued support for the development of Recording of Emergency Services Calls and Urgent-Care Environment (RESCUE), which will be an implementation of the National Emergency Medical Services Information System (NEMSIS).  Also planned is an ambulance stationing research project, the development of a spinal injury database, and a pilot project to reduce EMS delay time to the scene of crashes with a moving map display.  This will be accomplished by the implementation of the Mobile Officers’ Virtual Environment (MOVE) in EMS vehicles and the processing of trauma center and EMS run time data through CARE and ADVANCE.  MOVE will also provide the environment for the developments of the First Responder Solution Technique (FIRST), which has the goal of providing those arriving first on the scene of any emergency with injuries guidance as to optimal resources to call and the most effective target for transport.

- The Roadway Component involves a wide diversity of projects in support of the State’s IHSDM/HSM/SA initiatives.  This will include the integration of roadway features into CARE and the integration of Crash Modification Factors (CMFs) into the CORRECT system using the facilities of the CMF Clearinghouse.  To effectively locate crashes on the roadway, it is essential that ALDOT complete their various projects along these lines so that they can be integrated into eCrash and used by CARE to fully utilize its GIS displays capabilities.  Major advances in safety are anticipated with the implementation of the Roadway Improvement Safety Evaluation (RISE) system, which will leverage resources from routine maintenance projects into safety corridor projects along the segment being maintained.

- Vehicle Component plans include a statewide distribution network that will make vehicle information immediately available to all consumers of these data in the state, including the LETS system.  This will include projects on vehicle registration cards, vehicle data LETS integration, the Online Insurance Verification System (OIVS), and creating and effective TZD infrastructure.

- We have added an Integration and Information Distribution Component to the other functionally-oriented categories above in order to consider those projects that transcend and have the goal of integrating and/or producing/distributing information from several databases.  A major effort is proposed to populate the current Safe Home Alabama web portal so that it will integrate all of the information generated by all agencies and present it in one unified source to the traffic safety community.  An example of this is the proposed new Safety Portal that will be a hub for all traffic safety and related data analytics.  In addition, a large number of analytics projects that require the integration of multiple databases are included, such as the integration of eCrash and eCite databases with each other and with the driver history database to establish patterns of driver behavior that predict crash likelihood.  General TSIS management activities are also included in this component.

## 5.2  Project Specification

Projects have been proposed to address the most critical needs identified in the last assessment as well as other issues that have come to light since that time.  There are always far more projects proposed than there are resources to accomplish them.  The project detailed in the plan are those that have been determined by the TRCC to have the highest priority in this regard.  The following procedure is used to prioritize the proposed projects to reduce the set of projects that appear in the plan:

- Projects are solicited within each of the stakeholder agencies to assure that all potential projects are considered.

- Each of these projects are ranked according to the following criteria by all interested parties within the respective agencies:

  - Impact on the understanding and reduction of fatal and severe injury crashes (frequency and severity) over the lifecycle of the use of the product resulting from the project;

  - Relationship of the project to and its contribution to ongoing efforts with regard to cost, project momentum and synergy with ongoing projects;

  - Project cost – downside – what other projects are going to have to be sacrificed if this one is funded?  Also, total lifecycle costs must be considered, e.g., the necessity for users to purchase new equipment in order to implement the results of the project.

- Each of the agency stakeholder representative on the TRCC brings their recommendations to the TRCC meetings.  These are discussed in detail and the final set of projects to go into the plan is determined.

The final set of projects that appear in the plan are those with the highest priority and thus the greatest expectation of being implemented.  However, the sequencing of projects is itself an optimization problem, and there is no guarantee that any given project will be fully accomplished within the five year planning horizon.  Every attempt and commitment will be made, however, to assure that some progress is made on all of the projects in the plan.

The following is a statement of the projects planned within each of the six TSIS component areas and another added component for integration (overall TSIS management is considered within the Integration and Information Distribution Component):

#### 5.2.1.  Enforcement and Adjudication Component

  - Completion of the eCite roll-out.  This will result in a total roll-out of eCite and elimination of all paper citations statewide.  In the interim, a method will be sought to enable current paper tickets to be electronically submitted in a format that is compatible with eCite so that there is a comprehensive picture of the enforcement activity statewide.

  - DPS Motor Carrier integration with National FMCSA initiatives.  This project will support the DPS Motor Carriers unit in bringing about in-state regulation of motor carriers and the integration of these systems with the National FMCSA ongoing initiatives.  This includes at least five major software developments and respective training as given in the FMCSA documentation.

  - Full implementation of the Virtual Citation.  The development of the technology infrastructure necessary to support the full implementation of the recently passed legislation by the Alabama legislature that allows for electronic citations to serve as an “alternative approach” to tickets completed using the Alabama Uniform Traffic Citation form, including the development of the technology to print the notice to appear, as well as the technology and training to support electronic swearing.

  - Municipal electronic disposition system.  Some preliminary work on this has begun with regard to district courts and Commercial Motor Vehicles (CMV).  It needs to be further developed and applied at the district levels and then expanded into the municipal courts.

  - Upgrades to eCite.  There are a number of current issues with eCite that would justify a new version.  These issues will be the basis for a complete systems analysis and some re-design of the system to make it more effective in increasing officers’ productivity and presence in the field.

  - Citation and DUI Tracking System.  This system will display information on the current status of every citation that has been issued to date.  It will be able to respond to queries to determine if any given citation is (a) still in the electronic possession of the officer; (b) submitted but not adjudicated; (c) fully adjudicated or (d) reported to the driver history record.  A portal will be created and training conducted to enable officers in the field and judicial officials to see relevant MIDAS information on a given defendant so that (among other reasons) a repeat offense in another part of the state is not treated as a first offense.  It will also enable law enforcement to know whether a given individual is: (1) still on probation, (2) within the court referral program, or (3) in some other alternative treatment program.

#### 5.2.2.  Crash Component

- Develop infrastructure and provide training to support MapClick for improved crash location capability.  This is essential so that these project results (and/or other alternative approaches) can be applied to upgrade eCrash to include the ability of officers to obtain all required location data (coordinates, node numbers, link numbers, road names, road codes and milepoints) by a single click on a map available in the officer’s vehicle.  This will also result in a safety location portal for obtaining hotspots and related information.

- MapClick project.  This is a software system that will use as input available GIS-smart maps that have layers for coordinates, node numbers, link numbers, road names, road codes and milepoints.  The reporting officer (or other data collector) will be trained use existing GPS (if available) to obtain the general location of the crash (or any other event or object) on the map.  The data collector will then expand the map so that a precise location can be selected.  Clicking on that spot on the map will put all of the data into the record – the recording officer might check this data for general reasonableness, but generally will not be required to enter any other data into the record.  As long as the same maps are used to generate GIS outputs as are used in the underlying MapClick data collection perfect accuracy is not required, and thus it is not necessary for perfect maps to be generated in order for this system to work.  It is, however, necessary that all of the layers of data be present because if this system does not generate all of the required data it will not be accepted by the law enforcement community and will not be of much value since its use will not be universal.

- eCrash Upgrades.  A new version of eCrash recently integrated the “MapClick” capability as well as making major upgrades throughout the eCrash reporting system and added a variable for officers’ opinions for impaired driving.  A recent quality control effort has identified over a dozen faults in the current system and a list of the required upgrades is currently being assembled, including a number of edit checks.  It will also include a consideration of changes recently made in MMUCC.  One reported need is a variable that indicates damage to roadway inventory items (state or county property) in order to facilitate their replacements.

- CARE upgrades.  This ongoing product will result in a new CARE desktop interface, continual upgrading of the data, development of an enterprise CARE version for ALDOT internal use, and user training on these systems.  GIS upgrades will augment CARE’s current GIS map-generation capabilities with spatial and attribute filter dropdowns, the ability to export these filters and the ability to create templates for the various types of printers that might be employed in map production, including the consideration of the security and confidentiality issues that need to be resolved as this technology is deployed on web-based systems for engineering, law enforcement and other uses.  As a final innovation, it has been requested that CARE add an unofficial crash report that was in a completely different format from the official reports (that are sold) but contained all of the information on the crash report and was stamped for Engineering or Law Enforcement (Official Use) only.

- CARE scripting and dashboard capabilities.  Scripting will enable standard reports to be easily designed and then run from CARE.  It will essentially “capture” a series of CARE commands and save them into a program.  When a user wants to reproduce that functionality, this will be available by means of entering a command and parameters to direct the saved script.  The dashboard capability will enable local agencies to see a default presentation that they will be able to modify using the dashboard as another interface to their crash records.  This project was initiated in 2013 and has shown tremendous benefits; however, the current scripting capability is quite limited and needs to be expanded considerably.

- Upgrade to the Crash Facts document.  The Alabama Crash Facts Book was designed in the 1984 time frame, right after a change in the crash reporting form.  There are two needs that must be addressed at this time: (1) enabling the generation of this information on a routine basis directly out of CARE, and (2) preparing for the change in the crash reporting form that will accompany the implementation of the e-crash.  This project will accomplish both by putting into CARE a system by which a series of steps used to generate information can be incorporated into a script and re-used.  This will insure that the results are uniform and consistent from year to year, and that the information is totally up-gradable as new data formats are applied.  An upgrade in the 2013 time frame was applied to the 2012 data and has been very well received.  The need for additional fine tuning of this upgrade is expected.

- Total roll-out and use of eCrash.  The eCrash system was a major project that has obvious positive effects on timeliness, consistency, completeness, uniformity (including MMUCC compatibility), and efficiency of the state’s crash reporting.  It is imperative that the entire state either use eCrash or submit eCrash compatible data electronically so that the full utility of these innovations can be achieved.  An edict not to receive any additional paper forms after December 1, 2013 was a major positive step in this direction.  However, not all local agencies have responded to this edict.  As of March 2015, the proportion submitting paper forms was estimated at about 1.0%.

- Special location type exception reports.  This will generate reports similar to those in the Early Warning programs.  However, instead of the exception reports being criteria based, they will be based on a location type specification to the system (e.g., all workzones, recently completed improvements, wet-weather crash locations, etc.).  This project has been started and a number of exception reports have been generated, but the full potential of this capability has not yet been reached.  The project will include training of all users.

- Unreported crash incident reporting.  There are a number of incidents that should be reported but are not, the most notable probably being deer strikes.  In Michigan where it is required to report deer strikes in a crash report, over 30,000 per year are reported.  Alabama has more deer than Michigan, and yet in 2010 eCrash (85% of crashes reported) only recorded 2,162 crashes involving deer.  It is envisioned that this reporting capability could exist as a portal that would be initiated by voluntary reporting from the general public.

- Centralized CARE.   Historically, the CARE architecture has functioned as a stand-alone desktop application intended for one user on one machine.  The user was responsible for updating the CARE application and the CARE datasets.  The Centralized CARE or (CARE Enterprise) system will reduce the burden of effort on the users to maintain the latest versions of the CARE executable and datasets.  This is an on-going effort to change both CARE and the policies allowing access to centralized resources and data.  A significant step in that ongoing process is to train users on a new facility for them to know when new executables or data are available.  CARE10 is configurable to provide such notifications to users.

- FOCIS development.  The Formulated Ordering of Crashes at Intersections and Segments (FOCIS) tool will provide a visual summary of crashes at intersections of various types (traditionally referenced as a “collision diagram”).  The visual tool is valuable in providing engineers with a quick synopsis of the volume and type of crashes.  The determination of correct countermeasures and resource to apply requires a graphical summary report and a detailed report of the crashes at the intersection.  The FOCIS tool will be modified and users will be trained to provide improved specification, summary information, back-drops for different intersection types and improved reporting.

- Coordinate-based hotspot capability.  This project is concerned with developing new methods for determining hotspots based on the entered coordinates in the crash report.  With the implementation of MapClick and more sophisticated GPS techniques, the coordinate values are becoming much more reliable in being able to be used for crash location.  We currently know of no algorithms that have been developed to determine hotspots based totally on these coordinates (plus road code), but a comprehensive search for any research or development that has been done in this area will be conducted and this project will start with the best practices currently found to be used in the country.   One major problem in using coordinates only is that many roadways are so close together that there is no way to distinguish between them as to which roadway the hotspot would be on.  We plan to use a combination of the coordinates and the “ON” road to develop new algorithms.  While these will only be of partial use in the short term, we feel confident that the completeness and accuracy of the entered coordinates will be of such a quality in the near future (e.g., over the next five years) that this new methods will be clearly superior to those currently requiring translation to linear reference systems (LRS), which themselves are not perfectly accurate.  It is expected that this innovation will require considerable user training.

#### 5.2.3.  Driver Component

- DUI driver data intake and reporting system.  The eCite system uses MOVE to automatically query LETS to determine if the offender has a criminal record, outstanding warrants or protection orders, or is otherwise dangerous to the arresting officer (e.g., has offenses involving firearms).  This project will enlarge this capability to touch the MIDAS system for DUI information to provide a final link back to the field so that the officer can be trained to determine if the individual has a history of DUI offenses.  It will also provide the linkage from the officer to MIDAS to initiate or augment a current case record.  DUI (drugs and alcohol) accounts for up to 40% of fatalities in the state of Alabama, and this is seen as an information tool that will be a major deterrent to DUI.

- MIDAS offender completion validation.  This is an innovation of the MIDAS system to enable it to validate when an offender has completed his/her time of suspension or otherwise satisfied their alternative or traditional sanctions prior to re-instatement.

- Traffic safety incident data availability.  Comparable to the DUI driver data intake and reporting system discussed above, a system is needed to enable officers and law enforcement agencies to obtain full access to the ULTRA system.  ULTRA is a statewide initiative sponsored by ACJIC for recording, summarizing and reporting incidents before and after they arise to the status of resulting in arrests.

- LETS upgrades for traffic safety.  The Law Enforcement Tactical System (LETS) project has without question been the most successful law enforcement IT project conducted within Alabama in the past decade.  Under the direction of ACJIC, this project will take advantage of this momentum for traffic safety by integrating into LETS provisions by which serial traffic violators can easily be identified either directly by officers with networked laptops or PDAs, or by dispatchers as the officers check in.  Electronic citation information will enable officers to know if a driver has been given a recent warning or related citation.  LETS has also been quite successfully used at DUI and safety belt enforcement check stops.  Close to $1 million has already been invested into LETS; this allocation will be leveraged to assure that traffic safety application users are trained to obtain full use of the system.

- MOVE upgrades.  There are a number of additional components that can be added to MOVE to enable officers to be more efficient in their investigation and reporting activities.  For example, an insurance validation system would serve to provide a direct link from the officer in the field to a database indicating if the driver has liability insurance.  One major innovation to MOVE will be to add those components that are currently being developed for EMS so that all first responders are all have the same umbrella communications network.  ACJIC has also recommended several other upgrades to MOVE, including enhancements for real time data, map and building layout communications directly to field officers to deal with various emergencies (e.g., weather, hazardous materials, major traffic and other disasters, both natural and man-made).

- TZD education and research.  Public Information and Education is essential to the acceptance of driverless vehicles by the general public.  A series of PI&E spots are required to augment the advertising that has already begun in this direction by the manufacturers.  The spots will be more generic not only for conditioning the general public but for motivating them manufacturers themselves to take the lead in the development of this technology.  Part of this will include research to determine the ultimate role of the “driver” and the transitional role that will have to be played over the next half century in this evolution.

- Fraud detection method development.  Identity theft and other fraudulent activity with regard to drivers’ licenses and other traffic records are a major problem involving several agencies in maintaining this component of the traffic records system.  Envisioned is a review of the DL system by ALEA to determine the most effective current practices, such as the use of facial recognition.  For example, multiple engines could be developed to review all the DL photos for duplicates, which would surface one of the most common violations, that of a single person having multiple drivers’ licenses. In addition, similar automated methods should be developed for processing existing data to unearth other types of DL ID fraud.  It is important to realize that the proposed project to be overseen by the TRCC is that of determining the best approach toward an inter-agency cooperative effort in this regard and not operational fraud investigations, which are outside of the scope of TRCC responsibility.

#### 5.2.4.  EMS-Medical Component

- National Emergency Medical Services Information System (NEMSIS).  This project involves further development and continued implementation of the new Emergency Medical Service Information System (EMSIS) software.  The software will assure continued NEMSIS compliance.

- EMS-Trauma data integration through CARE.  A prototype system for the EMSIS data has proven its value in providing valuable information from this EMS run database.  To integrate trauma data into this system a two-phased approach will be performed: (1) the refinement of the current CARE/EMSIS system and the incorporation of trauma data under CARE, and (2) the integration of these datasets into a third dataset using key variables for case matching.  Consideration for the best match methods in Phase 2 and user training will be integral parts of the first phase.

- Additional medical database access.  This is a long-term project that must first be defined in terms of the various databases that could be made available to the state, e.g., trauma registry, electronic death reporting system (EDRS), emergency room and hospital discharge databases.  Current contacts within the Alabama Department of Public Health will be the starting point for a high level preliminary requirements document as a starting point for this project.  Ultimately records from volunteer fire departments might be included in this overall effort.

- Model Inventory of Emergency Care Elements.  Develop and populate a repository of the Model Inventory of Emergency Care Elements (MIECE) for the State.  The MIECE repository will be used to provide First Responders an inventory of emergency care resources in the occurrence of a mass casualty event.

- NEMSIS data entry.  Electronic EMS run system, Recording of Emergency Services Calls and Urgent-Care Environment (RESCUE).  As part of the NEMSIS effort and to assure more consistency and completeness of reporting, RESCUE will be a data entry system that will operate under MOVE to ultimately be deployed to all ambulances and other EMS units statewide to replace the current fragmented data entry system.  Training on the RESCUE system will also assure that the data elements gathered are NEMSIS v3 compliant.

- Supporting software for RESCUE.  A number of supporting software modules will be needed to implement RESCUE.  These deal primarily with the interfaces to other systems currently receiving data from or providing data to the existing EMS run data entry system.

- The First Responder Solution Technique (FIRST) project seeks to provide Law Enforcement (LE) agencies with quick, accurate, and location-aware inventory of available emergency medical assistance facilities.  A primary goal of the FIRST project is to provide this inventory to LE in the case of mass-causalities in rural areas of Alabama.  The project has collected a set of geo-located data providing medical facilities in the state from which a compact shape-file was developed for deployment in MOVE), which provides the MapClick interface.  The integration of a geo-located emergency medical facilities layer in MapClick provides LE the ability to visually determine the nearest appropriate facility.  This project also evaluated the available Alabama emergency medical assistance facilities inventory to the Model Inventory of Emergency Care Elements (MIECE) data standard developed by the National Association of State EMS Officials (NASEMSO) in March 2011.  The FIRST project will also evaluate the feasibility of providing LE with routing information from their current location to a selected facility.  Plans are to continue to enhance this capability so that it can reach its full potential over the next five years.

#### 5.2.5.  Roadway Data Systems Component

- Statewide roadway data inventory.  The state (including both ALDOT and many local jurisdictions) has spent millions of dollars on the creation and storage of roadway data.  Yet, when a preliminary analysis was performed to determine the availability of the data for IHSDM/HSM implementation, it was found that there is no central repository of these data, nor is there even a centralized data dictionary so that it could be determined which data elements even exist.  A critical first step is to create such a data dictionary that would list the data elements, where they are created, who is responsible for their storage and update, and the current use to which they are being employed.  Without such a document any further data gathering might be found to be unnecessarily redundant, and there would be no hope that the current data will ever be fully employed in the IHSDM/HSM efforts.  While this effort should begin with the data that exists for state, federal and Interstate (i.e., mileposted) routes, it should not be limited to these routes, recognizing that in 2009 about 46% of fatalities occurred on county roads and city streets.

- IHSDM/HSM implementation project.  This project is currently in its preliminary investigation stages in order to formulate a plan for the implementation of IHSDM, HSM, and Safety Analyst.  It is expected that over the next five years that these systems will be an integral part of the design and roadway improvement functions throughout the state.

- Roadway Issue Dispatch (RID) roll out.  This project has created an automated form that is an add-on to the current law enforcement MOVE system.  It give polices officers that have MOVE the capability to report any roadway conditions that could be considered as hazardous.  For state, Federal and Interstate roadways, this information is immediately forwarded to the appropriate person within ALDOT for immediate remedial action.  The project will determine and implement the most effective disposition of forms completed and electronically submitted by local law enforcement.  The form is available to DPS but there needs to be training to assure that the systems rolled out will be implemented by local law enforcement agencies.

- Develop and populate a repository of the Model Inventory of Roadway Elements (MIRE) for state routes.  Over the course of this plan complete 80% of the elements for at least 80% of state routes.  Develop a plan for population of MIRE for all public routes.   Relate the MIRE data to crash data in the CARE system for analysis and consideration of roadway engineering data in the state traffic safety program.

- Roadway Improvement Safety Evaluation (RISE).  This project is in its infancy; its goal is to create economies of scale and safety uniformity within the roadway system.  This will be accomplished by leveraging funds already dedicated (required) to be spent for roadway maintenance to also serve safety interests.  That is, while the crews are in the field doing maintenance they will be called upon to perform consistent safety upgrades along the entire corridor where they are working.  This systematic optimization system is seen to be a revolutionary approach toward roadway safety improvements that we know of no other state using.

#### 5.2.6.  Vehicle Component

- Vehicle registration cards.  A vehicle registration card is as important as a license card when it comes to collecting accurate data.  Currently the drivers’ license card is swiped to provide data for eCite and eCrash.  A vehicle registration card would pay its way very quickly in terms of saved officer time and nearly perfect data accuracy, and it would go a long way toward countering vehicle theft.

- Vehicle data LETS integration.  This project would take the current improved and timely data that is being obtained from the Motor Vehicle Title, Registration and Insurance Portal (MVTrip) and assure that it is available to all officers in the field on a timely basis.

- Online Insurance Verification System (OVIS).  OIVS is an online system to determine conformance with the State mandatory insurance law.  It is integrated with LETS (within MOVE) so that officers can be trained to have access to the relevant information at the roadside.  This system is in need of continual updates that are surfacing as it is being rolled out and implemented statewide.

- Effective TZD infrastructure.  See CARE ETL development below under Integration; specifically for the crash-vehicle data integration.  Toward Zero Deaths (TZD) can only become a reality if ultimately vehicles are equipped with the technology that essentially eliminates any possibility of a crash.  This is not a pipe dream; effective prototypes in this direction have been demonstrated reflected by some jurisdictions approving the use of driverless vehicles.  This element of the plan is to establish the fact that Alabama will use all of the data resources at its disposal to support this effort and to make TZD a reality in the shortest time possible.

#### 5.2.7.  Integration and Information Distribution Component

This component contains the management elements essential to maintaining and effective integrated TSIS effort.  Because the distribution of information usually requires this integration, we combine with it those projects that are dedicated to information distribution in general.

- SafeHomeAlabama.gov.  This web portal includes all state agencies, the legislature’s newly re-constituted State Safety Coordinating Committee, and all known service groups.  Its goal is to be totally comprehensive in keeping the entire traffic safety community aware of the most recent developments in traffic safety both in Alabama and Nationally.  Much of the information generated will be directly obtained from the TSIS given in the plan.  The rationale behind this web portal is that it is of no use to gather data unless it can be translated into useful information for countermeasure development.  This is the first formal statewide system for distributing traffic safety information.  While a prototype of the portal is currently in place and being updated by about 30 SHA Associates, the site needs further enhancement and continued effort to see that it is maintained with up-to-date information.  This project will be extended in this plan to include publicizing and linking to what we define to be the “Safety Portal.”  See the Safety Portal project below.

- TSIS Coordination.  The state has never had the resources to employ a formal full-time TSIS coordinator.  The function has been performed by the Traffic Records Coordinating Committee, with the Chair providing the coordination functions assisted by the ADECA staff.  Examples of the TSIS Coordination responsibilities include: (1) Administer the allocation of the Section 405c funds, including the performance of full effectiveness and administrative evaluations of all activities within the TSIS Strategic plan, whether Section 405c-supported or not; (2) Generally promote and be a champion for the integration of data and information systems among all of the involved departments; (3) Survey nationally TSIS innovations and make them known to the respective subject matter experts within Alabama; (4) Update the TSIS Strategic Plan on at least a semi-annual basis; (5) Be the executive secretary and facilitate the activities of the TRCC; and (6) Assure the continued enhancement and maintenance of information within SafeHomeAlabama.gov.  The state will make increased efforts to get the State Safety Coordinating Committee involved in providing additional coordination among the various entities that have traffic records responsibilities.

- Mobile Officers’ Virtual Environment (MOVE).  This is the basis for bringing together all of the systems currently used by field law enforcement officers, including eCite, eCrash, officers’ logbook, roadway issues reports, and all of the paperless office upgrades being made for DPS and local agencies.  MOVE will be upgraded to apply to several more applications and to operate more effectively with current applications.  In addition, MOVE will be extended so that it can operate within EMS units to support a number of EMS applications, including the new RESCUE data entry system.  Training will be necessary to assure that the full benefits of this system are obtained.

- Mobile device technology.  Listed under the Integration component because it affects all of the data entry and query systems within all other components.  This will involve porting the current systems to advanced mobile devices such as iPads, iPhones, and other devices operating under the Android and other mobile device operating systems.

- Data-Driven Approaches to Crime and Traffic Safety (DDACTS).  This approach, which is heavily supported by NHTSA and DOJ, seeks to take advantage of the officers in the field to assure that they are in the right place at the right time with the right equipment and software to perform whatever their immediate mission assignment might be; and to serve as the most effective deterrent to both crime and traffic violations.  This is the epitome of the benefits of integration of data from both the traffic safety and the criminal justice communities.  MOVE and CARE perform this data integration currently; DDACTS will create new applications of these data to further optimize officer activities and other law enforcement resources.

- CARE ETL development.  The CARE Extract-Translate-Load (ETL) component has been proven as an effective method for integrating databases that were originated for a variety of other purposes than traffic safety.  By creating a crash data linkage with related data, benefits are derived in both the traffic safety and the other involved disciplines.  The following are the immediate proposed integrations:

- Crash and roadway characteristics data.  This has been in prototype form for a number of years, proving the concept; it needs to be enlarged to cover the new data elements being collected within ALDOT.

- Crash and citation data.  Some prototypes exist along this line as well that compare the locations of crashes with the locations of citations, which is invaluable for officer location deployment decisions.

- Crash and EMS/Injury data.  This has been designed and is in its infancy; working prototypes are expected in the near future.

- Crash and vehicle data.  This is in need of design and development, the goal being to load the CARE datasets with vehicle characteristics that are now available via the tag number through the vehicle database to surface the Vehicle Identification Number, and then to use that number to engage the ETL to load the dataset with vehicle characteristics.

- Safety Portal.  This is a new web site that will be based on CARE/ADVANCE technologies.  Its goal is to enable those in the traffic safety community to access all of the information that they are authorized to consume under a single portal.  This will eliminate the need for a different portal for each agency.  It will be a consolidation of the current, largely distributed access that is required to the many disparate databases, and at the same time facilitate the capabilities to integrate two or more of these databases to produce information as discussed above.

### 5.3  TSIS Measurable Performance Indicators

A summary of the TSIS project goals in terms of measurable performance indicators is presented in the table at the end of this section.  Each of the projects is listed under the particular TSIS component to which they relate (e.g., crash, roadway, etc.).  In most cases IT projects only return their benefits when fully completed and deployed (e.g., a half-completed software development project generally does not produce any tangible benefits).  There are some exceptions in data development projects, but in most cases the goals established would be effective once the envisioned project to satisfy it was totally completed.

The state would have to perform studies that cost well beyond the total Section 405c allocation to the state in order to establish the benchmarks and performance metrics to any degree of reliability.  For this reason, the best estimates were used in many cases.  In some cases the ongoing and proposed projects have the objective of establishing data or systems that currently do not exist, and therefore the current benchmark is zero.  In other cases the benefits of the systems being developed will not be realized until these systems are deployed, and in these cases the metric is a degree of completion as opposed to some impact on the TSIS itself.  Thus, to the extent possible the metrics that are recommended in NHTSA document DOT HS 811 441 entitled "Model Performance Measures for State Traffic Records Systems" were used as the basis for the performance metrics given below.  In addition, the annual required Interim report that the State submits to NHTSA uses the metrics that are specified in the DOT HS 811 411 document.

| Projects | Goals (Measurable Performance Metric) |
| --- | --- |
| 1. Citations and Adjudication Projects 1a. Completion of the eCite roll-out 1b. DPS Motor Carrier Integration with FMCSA Initiatives 1c. Full implementation of the Virtual Citation. 1d. Municipal electronic disposition system. 1e. Upgrades to eCite. 1f. Citation and DUI Tracking System | 1. Citations and Adjudication Metrics 1a. Average time of getting citation information into the database: from several days to an average of less than one day. Proportion of agencies on eCite increased from 90% by 2% per year. 1b. From less that 50% current compliance to 100% compliance with Federal standards. 1c. For all eCite agencies, eliminate the need for paper tickets and officer swearing to the ticket in person at the courthouse. Reduce the time spent in printing to a few seconds and the time spent swearing to tickets to a few minutes per day. 1d. Five beta test municipalities after the first year of the start of development; at least 20 municipalities using the system after the second year. 1e. At least 10 upgrades completed and included in the next version release. 1f. Number and percentage of defendants for which data are available; functional portal under MOVE enabling officers to make queries on particular individuals; administrative capability to check the status of citation and defendants. |
| 2. Crash Component Project 2a. Develop infrastructure for improved crash location capability. 2b. MapClick project. 2c. eCrash upgrades 2d. CARE upgrades. 2e. CARE scripting and dashboard capabilities. 2f. Upgrade to the Crash Facts document. 2g. Total roll-out and use of eCrash. 2h. Special location type exception reports. 2i. Unreported crash incident reporting. 2j. Centralized (Enterprise) CARE 2k. FOCIS development 2l. Coordinate-based hotspot capability | 2. Crash Component Metrics 2a. Increase the completeness of maps from the current estimate of 60% by 10% per year so that the state is virtually covered by 2018. 2b. Increase the accuracy and completeness of the crash location entry for on-system (mileposted) locations from it current level of about 85% to at least 98%; for off-system segment locations, increase the accuracy from 0% to at least 98%. This can be measured by the number of cases that contain a 99999 in the node field, indicating that the node entered was either invalid or unknown. Reduce this from its current value of approximately 20% of cases to less than 2% of cases. 2c. Modify the eCrash data entry screens so that the data collected is over 96% MMUCC compliant; reduce time to enter locations from an average of 15 minutes to less than one minute with consistent accuracy as described in item 2b. 2d. Give users greater intuitive access to crash data and the information in the crash database thereby increasing the number of queries that they can perform without assistance from its current estimate of 60% to over 80%; and also increasing the number of queries that they will make from an average of 20 queries per user to well over 50 queries per user per year. 2e. Provide greater productivity in enabling users to save complex queries and reuse them, resulting in a 20% increase in the number of reports generated, and a 30% increase in the accuracy of queries since they will not have to be re-created periodically. 2f. Increase in the consistency of information presented from year to year; with the introduction of eCrash data this consistency dropped to about 90%; with this upgrade, the consistency will be 100%, providing users the capability to compare figures from year to year. 2g. MMUCC compliance increase from 85% to 100% for the eCrash data elements that are currently MMUCC compliant; consistency among all data elements; timeliness improvement from an average of about six weeks to be entered for the remaining paper forms to the eCrash delay of an average of 18 hours. 2h. Since the information being produced from these reports does not currently exist, there will be a 100% increase in information content from each type of exception report that will be created. 2i. These will create new data that does not currently exist; these data will generate information that cannot be derived from any current data source. At least 100 reports in the first prototype year. 2j. A functioning CARE system using a central server to store all executables and all datasets. 2k. Demonstration of a functional advanced collision-diagram generation system that is more advanced that any currently in existence. 2l. Demonstration of a hotspot capability that is based totally on GIS coordinates (and ON road code) independent of any linear reference system. |
| 3. Driver Component Projects 3a. DUI driver data intake and reporting system. 3b. MIDAS offender completion validation. 3c. Traffic safety incident data availability. 3d. LETS upgrades for traffic safety. 3e. Mobile Officer Virtual Environment (MOVE) Upgrades 3f. TZD education and research 3g. Fraud Detection Method Development | 3. Driver Component Metrics 3a. Law enforcement identification and apprehension of at least ten additional DUI offenders (per month) with outstanding warrants or court obligations. 3b. Currently this capability does not exist. The identification within the database of an estimated 30% of existing offenders within the database who have not completed their time of suspension or satisfied their alternative or traditional sanctions. 3c. This system and thus the information that it would generate does not currently exist. This will result in the availability to law enforcement of selected incidents that relate to traffic safety (e.g., habitual drug use). The first prototype should support 50-100 queries per day. 3d. This capability does not currently exist. It is expected that it will be able to detect hundreds of serial traffic violators per month based on an expected 50-100 queries per day. 3e. Most of the additional capabilities that enable officers to complete forms in their vehicles will require upgrades to the current MOVE system. Since this is a supportive role, it can only be measured in terms of the other systems that it supports. It is expected that at least ten new functions will be added to MOVE over the next five years, on average two per year. 3f. Number of PI&E messages broadcast; research report on the transitional role of the driver as the evolution toward driverless vehicles continues. 3g. Research report with recommendations for the state on the best approach to conduct multi-agency fraud detection and investigation. |
| 4. EMS-Medical 4a. NEMSIS 4b. EMS-Trauma data integration through CARE. 4c. Additional medical database access. 4d. MIECE Repository. 4e. RESCUE electronic EMS run data entry. 4f. Supporting software for RESCUE. 4g. Continued development of FIRST | 4. EMS-Medical 4a. Consistency: will maintain continued 100% NEMSIS compliance. 4b. Data access. None of the trauma data is accessible currently except through the writing of specialized queries and programs. This will make 100% of the data elements accessible to all computer literate users and thus increase accessibility by allowing data to be more readily imported and viewable by related health and safety organizations. This project will not start until 2016. 4c. Access available to one additional major database per year. 4d. Beta test of the MIECE data entry system completed by the end of the first year of project initiation. 4e. Beta test of the RESCUE system completed by the end of the second year from project initiation. 4f. Deployed operational support software; number of vendors who are using the supporting software. 4g. Number of components developed and deployed; reduced transport time; reduced number of patients who need to be forwarded to more appropriate facilities |
| 5. Roadway data systems projects 5a. Statewide roadway data inventory 5b. IHSDM/HSM implementation project. 5c. Roadway issue dispatch (RID) project. 5d. MIRE creation for state routes. 5e. Roadway Improvement Safety Evaluation (RISE) | 5. Roadway data system metrics 5a. Accessibility: currently these data are widely distributed and not accessible for IHSDM/HSM implementation. Add data elements to a IHSDM/HSM warehouse to make 20% of these data elements accessible per year so that at the end of the five year planning horizon 100% of the required data elements will be accessible. 5b. Improve the accuracy and the consistency of roadway modification benefit estimates by at least 50% over the planning horizon (e.g., if the accuracy is currently 80%, then a success would be in raising this accuracy to 90%), and thereby improving the optimization process so that an additional benefit of ten lives per year can be saved through roadway improvement projects. 5c. The addition of ten RID reports per month routed to either ALDOT or the appropriate county or city engineer. 5d. Ongoing progress of 20% of the data elements functional per year after initiation of the project. 5e. Beta test with at least five maintenance projects during the second year after project initiation. |
| 6. Vehicle Projects 6a. Vehicle registration cards. 6b. Vehicle data LETS integration. 6c. Online Insurance Verification System (OVIS) updates. 6d. Effective TZD infrastructure. | 6. Vehicle Performance Metrics 6a. Improve the accuracy of person and vehicle validation from its current value of approximately 90% to 98%. Implement cards statewide starting in 2018. 6b. Decrease the time that it takes an officer in the field to obtain vehicle and insurance verification from an average of six minutes to less than five seconds. 6c. Detect at least five areas where improvements can be made and develop them during the first year after project initiation. 6d. Documented interaction with TZD researchers resulting in the use of CARE and other tools and data to support and continue to develop the TZD infrastructure. |
| 7. Integration Projects 7a. SafeHomeAlabama.gov 7b. TSIS Coordinator 7c. Mobile Officers’ Virtual Environment (MOVE) upgrades to support integration. 7d. Mobile device technology. 7e. Data-Driver Approaches to Crime and Traffic Safety (DDACTS) 7f. CARE ETL development. 7g. Safety Portal | 7. Integration Performance Metrics 7a. Timeliness: add 10 more associates and pages to SHA and assure that information received is posted out on the web site within one hour of receipt. 7b. Presence of a functioning full-time TSIS coordinator, as evidenced by a complete documentation of all TSIS efforts and a complete knowledge of all co-efforts that are being performed in the TSIS community (i.e., any information systems effort that relates or can relate to traffic safety. 7c. Addition of at least three new functions to MOVE over the 2015 fiscal year. 7d. At least three applications ported over to smart phone or smart tablet technology within the 2015 fiscal year. 7e. Creation of at least one implemented DDACTS system by the end of FY 2015; e.g., the integration of crash, incident and citation data to determine optimal placement of law enforcement assets. 7f. One application functional every six months of the following: (1) crash-roadway; (2) crash-citation; (3) crash-EMS/injury; (4) crash-vehicle. 7g. The functioning portal with two major CARE/ADVANCE datasets added per year over the planning horizon. |